PHASE 9

Generator, Docs & Hardening

2 weeks  ·  Platform tier  ·  Spec Phase 9

SPECIFICATION REFERENCE   Spec Phase 9 (§19), §16 (Starter Project Generator), §18 (Documentation), plus §13/§14 hardening.

Deliver create-institution, complete the ten-guide documentation set, and harden the platform. One command generates a production-ready institution passing every gate and deploying to a live preview. This phase makes the platform reusable.

## Objectives

- Implement the create-institution CLI (§16) with industry presets and module selection.

- Ensure a generated project ships the full baseline: design system, CMS, auth, SEO, analytics, media, operations, docs, testing.

- Complete all ten documentation guides (§18) and example institutions.

- Harden performance (§14) and security (§13) to production budgets across the platform.

- Finalise release and migration workflows so institutions can upgrade safely.

## Deliverables

- tooling/create-institution CLI with the §16.1 generation flow.

- templates/ and examples/ (reference institutions per preset).

- All ten guides published and cross-linked; ADR index complete.

- Performance/security hardening pass with budgets enforced.

- Release + migration workflows and a platform-versioning scheme.

## Repository changes

- Add tooling/create-institution and templates/ for the generator to compose.

- Add examples/ reference institutions (clinic, school, store, firm, charity, research, SaaS, membership presets).

- Add release automation (versioned, changelog-driven) and migration scripts.

- Add analytics (consent-aware) and SEO defaults to the generated baseline.

## Folder structure

tooling/
└── create-institution/
    ├── prompts/        # name, industry, modules, brand, deploy
    ├── presets/        # industry → module presets
    ├── compose/        # assemble from templates/ + tokens
    └── verify/         # post-gen gate run
templates/              # project + file templates the generator composes
examples/
├── clinic/ school/ store/ firm/
├── charity/ research/ saas/ membership/
scripts/
├── release/           # versioned, changelog-driven releases
└── migrate/           # platform-version migrations

## Modules affected

- All modules — packaged for selective activation by the generator

- Analytics (§4.16) — baseline consent-aware analytics finalised here

- Settings — module presets consumed by the generator

## Interfaces to implement

- create-institution CLI (name → industry → modules → brand → deploy).

- settings.modules() — the generator writes the activation set.

- analytics.track/report — consent-aware baseline.

- Release/migration scripts (versioning, changelog, upgrade).

## External services

- Consent-aware, privacy-first analytics provider.

- Existing providers (Sanity, Cloudinary, Shopify, Stripe, Resend, search, AI) provisioned per activated module.

## Environment variables

| Variable | Purpose | Required |
| --- | --- | --- |
| ANALYTICS_WRITE_KEY | Privacy-first analytics (consent-gated). | yes |
| GENERATOR_TELEMETRY | Opt-in generator usage telemetry. | no |
| PLATFORM_VERSION | Pinned platform version for a generated project. | auto |

## Acceptance criteria

- create-institution generates a production-ready project that passes every gate and deploys to a live preview on first run.

- The generated baseline includes design system, CMS, auth, SEO, analytics, media, operations, docs, and testing with nothing left to hand-wire.

- Optional modules (Commerce, AI, Courses, Community/Membership, Booking, Research, Governance) are off by default and activate cleanly.

- All ten guides are complete; example institutions build green.

- Migration path lets an existing institution upgrade platform versions safely.

## Testing requirements

- Unit: generator prompt handling, preset resolution, template composition, brand-token application.

- Integration: generate each preset → project builds green → deploys to preview → baseline flows work.

- End-to-end: generate a store (Commerce on) and a clinic (Booking/Governance on); confirm both pass all gates.

- Migration: upgrade an example institution across a platform version bump without data loss.

## Production readiness checklist

☐  Generated projects pass typecheck, lint, a11y, visual-regression, performance, and security gates out of the box.

☐  Core Web Vitals within the 'good' band on the generated baseline (§14).

☐  Security baseline (§13) active by default in generated projects.

☐  Release workflow publishes versioned platform packages with changelogs.

☐  Migration guide + scripts verified against an example institution.

## Risks

| Risk | Description | Mitigation |
| --- | --- | --- |
| Generator drift | Generated projects diverge from platform standards over time. | Generator composes the same packages/standards; a post-gen gate run blocks non-conforming output. |
| Template rot | Templates lag behind module changes. | Templates consume module interfaces; CI builds every example on each release. |
| Upgrade breakage | Version bumps break existing institutions. | Semver + migration scripts + example-institution upgrade test in CI. |
| Perf regressions at scale | Baseline degrades as modules activate. | Budgets enforced per activated module; RUM monitoring in generated projects. |

## Dependencies

- All prior phases — the generator packages and activates everything built in Phases 0–8.

## Documentation updates

- Complete and cross-link all ten guides (§18), including Migration and Deployment.

- Publish the generator documentation (§16) and preset catalogue.

- Finalise the ADR index; ensure every major decision is recorded.

- Publish the Platform Guide's 'activate a module' and 'generate an institution' walkthroughs.

# Milestones & Tasks

## Milestone 9.1 — Generator core

OBJECTIVE   create-institution scaffolds a conforming project.

TASK 9.1.1 Implement the generation prompt flow Inputs Spec §16.1 (name → industry → modules → brand → deploy). Outputs The CLI collects name, industry, modules, brand tokens, and deploy target. Files created tooling/create-institution/prompts/ Files modified — Verification steps · The flow collects all five inputs. · Invalid inputs are rejected with guidance. Manual QA steps · Run the CLI; confirm each prompt and validation.

TASK 9.1.2 Implement industry presets Inputs Spec §16.1 industry presets; Settings module toggles. Outputs Presets mapping each industry to a sensible module activation set. Files created tooling/create-institution/presets/ Files modified — Verification steps · Each preset resolves to a valid module set. · Presets are overridable in the modules step. Manual QA steps · Select a clinic preset; confirm Booking/Governance suggested, Commerce off.

TASK 9.1.3 Implement template composition and brand-token application Inputs Spec §16.2; templates/; design-system tokens. Outputs The generator composes templates/ and applies brand tokens to theme the design system. Files created tooling/create-institution/compose/ · templates/ (base project) Files modified — Verification steps · Composition produces a buildable project. · Brand tokens theme the output. Manual QA steps · Generate with a custom palette; confirm the theme reflects it.

TASK 9.1.4 Implement the post-generation gate run Inputs Spec §16.2 definition of production-ready. Outputs The generator runs all gates and a preview deploy; it fails loudly if any gate fails. Files created tooling/create-institution/verify/ Files modified — Verification steps · A generated project passes all gates. · A forced failure is surfaced clearly. Manual QA steps · Generate a project; confirm it builds green and deploys to a preview automatically.

## Milestone 9.2 — Baseline, analytics & examples

OBJECTIVE   Every generated project ships the full baseline; examples prove it.

TASK 9.2.1 Finalise the consent-aware analytics baseline Inputs Spec §4.16 (privacy-first, consent-gated, no PII). Outputs analytics.track/report in the baseline, consent-gated with no PII by default. Files created packages/adapters/analytics-* · baseline analytics wiring Files modified templates baseline Verification steps · Analytics respects consent. · No PII in events by default. Manual QA steps · Decline consent; confirm no tracking fires.

TASK 9.2.2 Add SEO and metadata defaults to the baseline Inputs Spec §6.1 SEO; §14 performance. Outputs Per-document and global SEO/metadata defaults in generated projects. Files created — Files modified templates baseline (SEO defaults) Verification steps · Generated pages have correct metadata. · Sitemaps/robots present. Manual QA steps · Generate a project; inspect metadata and sitemap output.

TASK 9.2.3 Build example institutions (batch 1) Inputs Spec §16 presets; examples/. Outputs clinic, school, store, and firm example institutions building green. Files created examples/{clinic,school,store,firm}/ Files modified — Verification steps · Each example builds and passes gates. · Each demonstrates its preset. Manual QA steps · Build each example; confirm gate pass and preset behaviour.

TASK 9.2.4 Build example institutions (batch 2) Inputs Spec §16 presets; examples/. Outputs charity, research, saas, and membership example institutions building green. Files created examples/{charity,research,saas,membership}/ Files modified — Verification steps · Each example builds and passes gates. · CI builds all examples on release. Manual QA steps · Build each example; confirm gate pass and CI coverage.

## Milestone 9.3 — Hardening, docs & release

OBJECTIVE   Production hardening, complete documentation, and safe upgrades.

TASK 9.3.1 Performance hardening pass Inputs Spec §14 (Core Web Vitals, budgets, caching, edge). Outputs Baseline meets CWV 'good' band; budgets enforced; caching/edge tuned. Files created — Files modified baseline performance config · CI performance gate Verification steps · CWV within budget on the baseline. · Budget breach fails CI. Manual QA steps · Run Lighthouse/RUM on a generated project; confirm the 'good' band.

TASK 9.3.2 Security hardening pass Inputs Spec §13 (full baseline active by default). Outputs Security baseline verified across generated projects; dependency/supply-chain scanning enforced. Files created — Files modified baseline security config · CI security gates Verification steps · Generated projects pass the security gate set. · Dependency scan blocks known-vulnerable packages. Manual QA steps · Generate a project; run the security suite; confirm a clean pass.

TASK 9.3.3 Complete the ten documentation guides Inputs Spec §18 documentation set (stubs from Phase 0). Outputs All ten guides complete, cross-linked, with a finished ADR index. Files created — Files modified docs/guides/* · docs/adr index Verification steps · Each guide's scope matches §18. · Cross-links resolve; ADR index complete. Manual QA steps · Review each guide against its §18 scope; follow cross-links.

TASK 9.3.4 Implement release and migration workflows Inputs Spec §18 (Migration Guide); §15 release workflow. Outputs Versioned, changelog-driven releases; migration scripts; an example-institution upgrade test. Files created scripts/release/ · scripts/migrate/ Files modified Migration Guide · CI (example upgrade test) Verification steps · A release publishes versioned packages + changelog. · An example upgrades across a version bump without data loss. Manual QA steps · Cut a test release; upgrade an example institution; confirm no data loss.